## Plan To-Do
Week of | Week theme | Work Item | Status
6/15/2026 | Establish business | Research targeted customers | Closed
6/15/2026 |  | File LLC and apply EIN | Closed
6/22/2026 | Networking | Research targeted customers | In progress
6/22/2026 |  | Build a website | Not started

## Work Records
Date | Work Item | Task | Category | Hours | Notes
6/16/2026 | Research targeted customers | Built list of 20 target companies | Sales | 3.5 | Healthcare first
6/17/2026 | File LLC and apply EIN | Filed LLC with the state | Administration | 2
6/23/2026 | Research targeted customers | Outreach emails to first 5 targets | Sales | 1.5

## How to import
HOW TO IMPORT
1. Replace the YELLOW example rows with your data (delete any you don't use).
2. In Tasks Tracker: sign in → Backup → Import from Excel (.xlsx) → pick this file → confirm.
Import replaces whatever is in the app, and the result syncs to your Google Drive.
THE ONLY RULE THAT MATTERS
Type each work item's name EXACTLY the same everywhere it appears — that's how plan rows
and work records get linked together. WI# numbers are assigned automatically.
GOOD TO KNOW
Week of: any date inside that week works — it snaps to the week's Monday (weeks run Mon–Sun).
Week theme: an optional label for the week (e.g. 'Establish business'). It only needs to appear
on one row of that week — leave it blank on the others.
Status: Not started / In progress / Blocked / Closed ('done' also works). Progress % is set
automatically from status; fine-tune it in the app afterward.
Category: enter it in Work Records — it only needs to appear once per item, and it carries
over automatically after that. New categories are created automatically.
Hours: decimal numbers, e.g. 1.5.
An item worked over several weeks = one plan row per week, same item name.